## Sheet1
Members | INITIAL
JLM | JLM
Aysen | AY
Ryan | RY
Jonathyn | JO
|  | Page | Detail | Additional Info | Weight | Assignee
|  | Main Page | Will be a central hub for navigating to the other parts of the website as well as displaying basic information about chitchat | Mostly design driven and meant to entice the customer | 3 | RY
|  | Manage Account | Allows the user to input basic information as well as purchase information | Include possible previous orders; Displays Active Orders | 4 | JO
|  | Order Coffee/Baked good | Location where the user can add to cart/edit items sold by chitchat | Will feed from database informaiton of current products sold | 3 | JLM
|  | Buy Merch | Similar to Order Food but will be a bit more simple |  | 2 | JLM
|  | Shopping Cart | A list of items that have been added for purchase. | Should be faily simple but will need to include a price breakdown from all sources (including customization and tax) | 3 | AY
|  | Checkout | A place where the user can complete and send to order | If we decite to primarily run off of clover, we will only need to access the api and not user clover's interface | 4 | JO
|  | Admin Order Interface | Displays current orders and allows the barista to edit where the coffee is at in the process and complete orders | will need to continually pull for data to ensure that order updates are pulled/pushed within seconds | 4 | AY
|  | Admin Web Configuration | Product editing/adding tool that allows admin to make changes to the menu |  | 3 | RY
|  | TOTAL POINTS | Points per person
|  | 26 | 6.5

## Sprints
| Main Page | Manage Account | Order Coffee/Baked good | Buy Merch | Shopping Cart | Checkout | Admin Order Interface | Admin Web Configuration
1 | Design look | Design Look | Design look | Design Look | Design look | Design Look | Design look | Design Look
2 | build page layout (web) | build page layout (web) | build page layout (web) | build page layout (web) | build page layout (web) | build page layout (web) | build page layout (web) | build page layout (web)
3 | Connect website | Build UI and create documentation for layout of attributes and class/ID name | Build a layout to allow for a continually growing amount of content | Build a layout to allow for a continually growing amount of content | Connect to database of items in cart and itemize price | Utilize Clover API and make Request to CRUD orders | Build content for pulling from database every few seconds to ensure quick turnover time, may need to receive orders from Clover | Build out options
4 | Consult customer about full main page functionality | Build in Credit card connections | Discuss with owner on how we plan to seciton the store in terms of dring type and bake good type | Add Add-to-cart functionality | Connect to checkout and pass all needed data for transaction | If not clover, utilize STRIPE | Add, CRUD Options to allow baristas to make edits to orders. | Create Database functionality to Ensure new items are posted immediately.
|  | Add, ability for visualize current orders and make edits or deletes the request if the Barista has not started the order. | Add Add-to-cart functionality